## Detail
[5 empty] | 266 | 33.25 |  | 33.25 | 46.55
Sprint | Section | Part | Description | Extra info | Hours | Days | Over-ruled | Total Dev | Total days
| Setup | Third-party libraries | Investigate which (third-party) libraries are required and implement them. | Assumption: No specific libraries are a hard requirement to use (we can use AutoMapper, Polly for convenience) | 6 | 0.75 |  | 0.75 | 1.05
| Setup | Setup API communication with authentication | Using HTTP client factory. | Assumption: The authentication is shared across each product API (verify) | 24 | 3 |  | 3 | 4.2
| Setup | Configuration in API developer portal | https://documentation.ibanity.com/ | Assumption: We only need to register one app | 6 | 0.75 |  | 0.75 | 1.05
| Setup | Configure Webhooks | https://documentation.ibanity.com/webhooks | Question: The goal of the webhooks is not fully clear from the code | 24 | 3 |  | 3 | 4.2
| XS2A | Convert and test 14 services | Use Java to C# converter for each class/interface and fix the code until it works. Bank authentication might take some extra effort. | Assumption: Java to C# converter can be used | 80 | 10 |  | 10 | 14
| Isabel connect | Convert and test 8 services | Use Java to C# converter for each class/interface and fix the code until it works. | Assumption: Java to C# converter can be used | 40 | 5 |  | 5 | 7
| Ponto connect | Convert and test 14 services | Use Java to C# converter for each class/interface and fix the code until it works. | Assumption: Java to C# converter can be used | 70 | 8.75 |  | 8.75 | 12.25
| Documentation | Update readme for developers | Write a readme for the .NET implementation, similar to the one that exists for Java. |  | 8 | 1 |  | 1 | 1.4
| Deployment | Pipelines for building and automated testing, and making code available publicly (Github). |  |  | 8 | 1 |  | 1 | 1.4
General assumption: Only XS2A, IsabelConnect and Ponto connect require an implementation (based on the Java wrapper source code)
General assumption: ~404 .java files to convert
General assumption: refactoring to .NET standards, migration API approach, is included.

## Planning
|  |  | Volgens Total |  | 0% | 10% | 25% | 0% | 5% | 17% | 57%
|  |  |  | 100% | 0% | 10% | 25% | 0% | 5% | 17% | 57%
|  |  |  | Dev | Arch | PM | Test | Analyse | Doc | Cont |  | UX |  |  |  | 0.04125 | 0.75
|  |  | Estimated | 33.25 | 0 | 3.325 | 8.3125 | 0 | 1.6625 | 7.9135 | 54.4635 | 0
|  |  | Planned | 33 | 0 | 3 | 8 | 0 | 2 | 8 | 54 | 0 | 0 | 0 |  | 1.8975 | 3.1875
|  |  |  | 100% | 0% | 9.091% | 24.24% | 0% | 6.061% | 17.39% | 0.4635 | 0
|  |  |  | Dev | Arch | PM | Test | Analyse | Doc | Cont |  | UX | WCAG | Security | #persons | Daily | SR | Total - FTE | Dev | Arch | PM | Test | Analyse | Doc | Ux
2019-10-21 | 5 | 2022-03-01 | week 1 | 4 |  | 0.5 | 0.5 | [7 empty] | 1 | 0.20625 |  | 1.0413 | 0.8 | 0 | 0.1 | 0.1 | 0 | 0 | 0
2019-10-28 | 6.5 | 2022-03-08 | week 2 | 5 |  | 0.5 | 1 | [7 empty] | 1.3 | 0.26813 |  | 1.3536 | 1 | 0 | 0.1 | 0.2 | 0 | 0 | 0
2019-11-04 | 6.25 | 2022-03-15 | week 3 | 5 |  | 0.25 | 1 | [7 empty] | 1.25 | 0.25781 | 0.975 | 1.4966 | 1 | 0 | 0.05 | 0.2 | 0 | 0 | 0
2019-11-11 | 6.5 | 2022-03-22 | week 4 | 5 |  | 0.5 | 1 | [7 empty] | 1.3 | 0.26813 |  | 1.3536 | 1 | 0 | 0.1 | 0.2 | 0 | 0 | 0
2019-11-18 | 6.25 | 2022-03-29 | week 5 | 5 |  | 0.25 | 1 | [7 empty] | 1.25 | 0.25781 | 0.9375 | 1.4891 | 1 | 0 | 0.05 | 0.2 | 0 | 0 | 0
2019-11-25 | 5.5 | 2022-04-05 | week 6 | 4 |  | 0.5 | 1 |  |  | 1 |  |  |  |  | 1.1 | 0.22688 |  | 1.1454 | 0.8 | 0 | 0.1 | 0.2 | 0 | 0 | 0.2
2019-12-02 | 5.25 | 2022-04-12 | week 7 | 3 |  | 0.25 | 1 |  | 1 | 2 |  |  |  |  | 1.05 | 0.21656 | 0.7875 | 1.2508 | 0.6 | 0 | 0.05 | 0.2 | 0 | 0.2 | 0.4
2019-12-09 | 3.25 | 2022-04-19 | week 8 | 1 |  | 0.25 | 1 |  | 1 | 4 |  |  |  |  | 0.65 | 0.13406 | 0.4875 | 0.77431 | 0.2 | 0 | 0.05 | 0.2 | 0 | 0.2 | 0.8
2019-12-16 | 1 | 2022-04-26 | week 9 | 0.5 |  |  | 0.5 |  |  | 1 |  |  |  |  | 0.2 | 0.04125 |  | 0.20825 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.2
2019-12-23 | 0.5 | 2022-05-03 | Go live | 0.5 | [10 empty] | 0.1 | 0.020625 |  | 0.10413 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
2019-12-30 | 0 | 2022-05-10 | week 11 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: scrum = 20min max

## Total
1
FPA |  |  | Planned
Development |  | 33.25 | 33
Architecture | 0% | 0 | 0
Project Management | 10% | 3.325 | 3
Testing | 25% | 8.3125 | 8
Analysis | 0% | 0 | 0
Technical documentation | 5% | 1.6625 | 2
Sum uplift on development hours | 40% | 46.55
Contingency | 17% | 7.9135 | 7.82
UX |  |  | 0
Subtotal |  | 54.4635 | 53.82 | Days
Total days |  | 53.82
Dev/Test (€/d) | 700 | 41 | 28700
Analist/Training/documentation (€/d) | 760 | 2 | 1520
PM/Arch (€/d) | 880 | 3 | 2640
Contingency (€/d) | 700 | 7.82 | 5474
Subtotal |  |  | 38334
Avg rate €/d |  |  | 712.2631
WCAG | 700 | 0 | 0
Agile ceremonies | 710 | 5 | 3550
Security | 1066 | 0 | 0
Threat-model | 5550 | 0 | 0
Performance testing | 850 | 0 | 0
Total |  | 58.82 | 41884